## All Sprints Master
Sprint | Compartment | Task ID | Task / Activity | Lead Owner | Target Date | Status | Expected Outcome | Actual Outcome | Blocker | Delay Reason | RAG
Sprint 1 | Compartment 1: Market, Intake & Client POCs | S1.1 | Draft Business $\rightarrow$ Tech Intake Format v1 | Prakhar | Thu, Sept 3 (Day 3) | [-] In Progress | Standard intake format defining: Who $\rightarrow$ Wants What $\rightarrow$ Context $\rightarrow$ POC $\rightarrow$ Scale $\rightarrow$ Tech expectation | Creating client contact intake sheet in Google Sheet format | None | None | 🟡
Sprint 1 | Compartment 1: Market, Intake & Client POCs | S1.2 | Collect client context: **Orane** | Yashvi | Fri, Sept 4 (Day 4) | [ ] Planned | Complete background, target audience, scale, missing items identified | Will start today | None | None | ⚪
Sprint 1 | Compartment 1: Market, Intake & Client POCs | S1.3 | Collect client context: **College Vidya** | Yashvi | Fri, Sept 4 (Day 4) | [ ] Planned | Complete admissions/CRM context, scale, integration requirements | Will start today | None | None | ⚪
Sprint 1 | Compartment 1: Market, Intake & Client POCs | S1.4 | Collect client context: **Chitkara** | Yashvi | Fri, Sept 4 (Day 4) | [ ] Planned | Complete placement/academic scope, 100-student cohort context | Will start today | None | None | ⚪
Sprint 1 | Compartment 1: Market, Intake & Client POCs | S1.5 | Define schema & draft **Product Catalogue v1** | Prakhar | Fri, Sept 4 (Day 4) | [ ] Planned | Product, buyer, use case, maturity, demo readiness, limitations | - | None | None | ⚪
Sprint 1 | Compartment 1: Market, Intake & Client POCs | S1.6 | Define schema & seed **Capability Registry v1** | Yashvi | Fri, Sept 4 (Day 4) | [x] Completed | Core AI capabilities (RAG, Eval, Voice, Parser) mapped to products | Need to update it at end of the month | None | None | 🟢
Sprint 1 | Compartment 2: Product, In-House LMS & Demo Stabilisation | S1.7 | Freeze P0 product/module list & assign owners | Shubham | Wed, Sept 2 (Day 2) | [x] Completed | Final P0 list with named module owners across both suites | - | None | None | 🟢
Sprint 1 | Compartment 2: Product, In-House LMS & Demo Stabilisation | S1.8 | Triage all P0 bugs across live suites by severity | Shubham | Wed, Sept 2 (Day 2) | [ ] Planned | Critical / blocker bug list ready with reproduction steps | - | None | None | ⚪
Sprint 1 | Compartment 2: Product, In-House LMS & Demo Stabilisation | S1.9 | **Fix critical / blocking P0 bugs on staging** | Rohan | **Fri, Sept 4 (Day 4)** | [-] In Progress | **Critical blocker issues cleared in Week 1; verified** | Email delivery bug fixed; info email account migrated; testing pipeline | GPT credit exhausted | None | 🔴
Sprint 1 | Compartment 2: Product, In-House LMS & Demo Stabilisation | S1.10 | Define clean demo environment requirements | Shubham | Fri, Sept 4 (Day 4) | [ ] Planned | Spec sheet for dummy student rosters & sanitized CRM leads | - | None | None | ⚪
Sprint 1 | Compartment 2: Product, In-House LMS & Demo Stabilisation | S1.11 | **Demo #1: Sales & Admin Suite Walkthrough** | Prakhar | **Thu, Sept 3 (Day 3)** | [ ] Planned | **Weekday baseline demo of Sales & Admin Suite** | - | None | None | ⚪
Sprint 1 | Compartment 2: Product, In-House LMS & Demo Stabilisation | S1.22 | Sales Suite technical documentation & research plan | Shubham | Fri, Sept 4 (Day 4) | [x] Completed | Technical architecture doc & generalized setup plan | Sales Suite prototype presented (DB separation & lead import); backend analysis underway | None | None | 🟢
Sprint 1 | Compartment 3: Cloud, Cost & Internal Automation | S1.12 | Inventory current GCP projects, services & VMs | Rohan | Thu, Sept 3 (Day 3) | [!] Blocked | Complete GCP infrastructure inventory with instance sizes | - | GPT credit exhausted | None | 🔴
Sprint 1 | Compartment 3: Cloud, Cost & Internal Automation | S1.13 | Inventory AWS accounts/services used by AI Labs | Rohan | Fri, Sept 4 (Day 4) | [ ] Planned | Complete AWS inventory (S3, compute, IAM) | - | GPT credit exhausted | None | 🔴
Sprint 1 | Compartment 3: Cloud, Cost & Internal Automation | S1.14 | Master inventory of AI/API keys, models & endpoints | Rohan | Fri, Sept 4 (Day 4) | [ ] Planned | All third-party AI keys mapped to product modules | - | GPT credit exhausted | None | 🔴
Sprint 1 | Compartment 3: Cloud, Cost & Internal Automation | S1.15 | Collect top repetitive workflows across MAS departments | Rohan | Fri, Sept 4 (Day 4) | [ ] Planned | Departmental automation intake list (Problem $\rightarrow$ Effort $\rightarrow$ Value) | - | GPT credit exhausted | None | 🔴
Sprint 1 | Compartment 3: Cloud, Cost & Internal Automation | S1.16 | **Build & configure MAS Slack Standup Bot v1.0** | Yashvi | **Thu, Sept 3 (Day 3)** | [-] In Progress | **Personal DMs, dropdown modal, 7:45 PM summary & 2-way sync** | slack bot formatting fixing in progress | None | None | 🟡
Sprint 1 | Compartment 3: Cloud, Cost & Internal Automation | S1.17 | **Test & pilot Slack Standup Bot with core team** | Yashvi | **Fri, Sept 4 (Day 4)** | [-] In Progress | **Live test during Friday standup & Friday review #1** | Testing daily summaries and improve the AI summarisation | None | None | 🟡
Sprint 1 | Compartment 4: Leadership, Compute & Enablers | S1.18 | Kick off QA Tester (contract/2-mo) hiring | Gaurav | Tue, Sept 1 (Day 1) | [-] In Progress | Active job description & candidate pipeline with HR | - | None | None | 🟡
Sprint 1 | Compartment 4: Leadership, Compute & Enablers | S1.19 | Kick off PM Intern (25 hrs/wk) hiring | Gaurav | Tue, Sept 1 (Day 1) | [ ] Planned | Active job description & candidate sourcing | - | None | None | ⚪
Sprint 1 | Compartment 4: Leadership, Compute & Enablers | S1.20 | Initial September GPU/compute sync with Sajan | Gaurav | Thu, Sept 3 (Day 3) | [ ] Planned | Compute vendor contacts & initial workload candidate list | - | None | None | ⚪
Sprint 1 | Compartment 4: Leadership, Compute & Enablers | S1.21 | **Weekly Product & Capability Review #1 (8:00 PM)** | Gaurav | Fri, Sept 4 (Day 4) | [ ] Planned | Review minutes, Week 1 bug fix verification & RAG audit | - | None | None | ⚪
Sprint 2 | Compartment 1: Market, Intake & Client POCs | S2.1 | Walkthrough Intake Process with Pranab Sir | Prakhar | Mon, Sept 7 (Day 7) | [ ] Planned | Business alignment on mandatory intake rules | - | None | None | ⚪
Sprint 2 | Compartment 1: Market, Intake & Client POCs | S2.2 | **Sign off Business $\rightarrow$ Tech Intake Format (M6)** | Prakhar | **Thu, Sept 10 (Day 10)** | [ ] Planned | **Joint intake format signed off; live for Fri, Sept 11** | - | None | None | ⚪
Sprint 2 | Compartment 1: Market, Intake & Client POCs | S2.3 | Conduct structured scoping call: **Orane** | Yashvi | Tue, Sept 8 (Day 8) | [ ] Planned | Scope v1 draft for Orane (scale, features, timeline) | - | None | None | ⚪
Sprint 2 | Compartment 1: Market, Intake & Client POCs | S2.4 | Conduct structured scoping call: **College Vidya** | Yashvi | Wed, Sept 9 (Day 9) | [ ] Planned | Scope v1 draft for College Vidya (CRM/voice needs) | - | None | None | ⚪
Sprint 2 | Compartment 1: Market, Intake & Client POCs | S2.5 | Conduct structured scoping call: **Chitkara** | Yashvi | Thu, Sept 10 (Day 10) | [ ] Planned | Scope v1 draft for Chitkara (100-student placement cohort) | - | None | None | ⚪
Sprint 2 | Compartment 1: Market, Intake & Client POCs | S2.6 | Consolidate 3 Client Scope v1 drafts | Yashvi | Fri, Sept 11 (Day 11) | [ ] Planned | 3 Scopes ready for technical feasibility review | - | None | None | ⚪
Sprint 2 | Compartment 1: Market, Intake & Client POCs | S2.7 | Finalize & format **Product Catalogue v1** | Prakhar | Fri, Sept 11 (Day 11) | [ ] Planned | Published catalogue ready for official release (Due Sept 14) | - | None | None | ⚪
Sprint 2 | Compartment 1: Market, Intake & Client POCs | S2.8 | Finalize & format **Capability Registry v1** | Yashvi | Fri, Sept 11 (Day 11) | [ ] Planned | Seed registry ready for official release (Due Sept 14) | - | None | None | ⚪
Sprint 2 | Compartment 2: Product, In-House LMS & Demo Stabilisation | S2.9 | **In-House LMS Architecture & Data Schema Design** | Shubham | Tue, Sept 8 (Day 8) | [ ] Planned | Technical architecture spec for replacing Graphy in Mr. Learn | - | None | None | ⚪
Sprint 2 | Compartment 2: Product, In-House LMS & Demo Stabilisation | S2.10 | **In-House LMS Core Build (Part 1: Course & Content Engine)** | Shubham | Fri, Sept 11 (Day 11) | [ ] Planned | In-house course structure, modules & video delivery service | - | None | None | ⚪
Sprint 2 | Compartment 2: Product, In-House LMS & Demo Stabilisation | S2.11 | Curate clean demo environment: **Learning Suite** | Shubham | Wed, Sept 9 (Day 9) | [ ] Planned | Seeded with safe, client-presentable student data | - | None | None | ⚪
Sprint 2 | Compartment 2: Product, In-House LMS & Demo Stabilisation | S2.12 | Curate clean demo environment: **Sales CRM** | Shubham | Thu, Sept 10 (Day 10) | [ ] Planned | Stripped of internal MAS lead data; clean CRM pipeline | - | None | None | ⚪
Sprint 2 | Compartment 2: Product, In-House LMS & Demo Stabilisation | S2.13 | **Demo #2: Learning Suite Walkthrough** | Yashvi | **Wed, Sept 9 (Day 9)** | [ ] Planned | **Weekday baseline demo of Learning Suite** | - | None | None | ⚪
Sprint 2 | Compartment 3: Cloud, Cost & Internal Automation | S2.14 | Identify idle, duplicate, orphaned cloud resources | Rohan | Mon, Sept 7 (Day 7) | [ ] Planned | Cloud cleanup action list (disks, IPs, test VMs) | - | None | None | ⚪
Sprint 2 | Compartment 3: Cloud, Cost & Internal Automation | S2.15 | Clean up unused resources & permissions in GCP/AWS | Rohan | Tue, Sept 8 (Day 8) | [ ] Planned | Reduced waste & cleaner cloud estate | - | None | None | ⚪
Sprint 2 | Compartment 3: Cloud, Cost & Internal Automation | S2.16 | Apply naming, ownership and cost tagging to cloud assets | Rohan | Wed, Sept 9 (Day 9) | [ ] Planned | Resources traceable by product and environment | - | None | None | ⚪
Sprint 2 | Compartment 3: Cloud, Cost & Internal Automation | S2.17 | Prototype token & latency tracking helper / middleware | Rohan | Thu, Sept 10 (Day 10) | [ ] Planned | Request-level token logging on suite endpoints | - | None | None | ⚪
Sprint 2 | Compartment 3: Cloud, Cost & Internal Automation | S2.18 | Score collected departmental automation workflows | Rohan | Fri, Sept 11 (Day 11) | [ ] Planned | Workflows ranked by effort, impact, hours saved | - | None | None | ⚪
Sprint 2 | Compartment 3: Cloud, Cost & Internal Automation | S2.19 | **Full live pod rollout of Slack Standup Bot** | Yashvi | **Mon, Sept 7 (Day 7)** | [ ] Planned | **100% daily standup updates captured via Slack DMs & synced** | - | None | None | ⚪
Sprint 2 | Compartment 3: Cloud, Cost & Internal Automation | S2.20 | **Add /standup-notes & weekend rollover handler** | Yashvi | **Thu, Sept 10 (Day 10)** | [ ] Planned | **Post-call highlight logger and weekend rollover features live** | - | None | None | ⚪
Sprint 2 | Compartment 4: Leadership, Compute & Enablers | S2.21 | Screen resumes & interview QA Tester candidates | Gaurav | Wed, Sept 9 (Day 9) | [ ] Planned | QA candidate shortlisted & evaluated | - | None | None | ⚪
Sprint 2 | Compartment 4: Leadership, Compute & Enablers | S2.22 | Screen resumes & interview PM Intern candidates | Gaurav | Wed, Sept 9 (Day 9) | [ ] Planned | PM Intern candidate evaluated | - | None | None | ⚪
Sprint 2 | Compartment 4: Leadership, Compute & Enablers | S2.23 | Extend offers for QA Tester and PM Intern | Gaurav | Fri, Sept 11 (Day 11) | [ ] Planned | Offers extended for Sept 21 onboarding | - | None | None | ⚪
Sprint 2 | Compartment 4: Leadership, Compute & Enablers | S2.24 | Define GPU model-serving architecture with Sajan | Gaurav | Thu, Sept 10 (Day 10) | [ ] Planned | API vs Self-hosted cost comparison note | - | None | None | ⚪
Sprint 2 | Compartment 4: Leadership, Compute & Enablers | S2.25 | **Weekly Review #2: Month 1 Mid-Point Sign-off** | Gaurav | Fri, Sept 11 (Day 11) | [ ] Planned | Intake sign-off confirmed; LMS Build Part 1 progress review | - | None | None | ⚪
Sprint 3 | Compartment 1: Market, Intake & Client POCs | S3.1 | **Publish Product Catalogue v1 (M5)** | Prakhar | **Mon, Sept 14 (Day 14)** | [ ] Planned | **Catalogue v1 complete & published for Business** | - | None | None | ⚪
Sprint 3 | Compartment 1: Market, Intake & Client POCs | S3.2 | **Publish Capability Registry v1 (M5)** | Yashvi | **Mon, Sept 14 (Day 14)** | [ ] Planned | **Registry v1 seeded & published for Business** | - | None | None | ⚪
Sprint 3 | Compartment 1: Market, Intake & Client POCs | S3.3 | Conduct technical feasibility review on 3 client scopes | Shubham | Wed, Sept 16 (Day 16) | [ ] Planned | Feasibility note & rough effort estimate per client | - | None | None | ⚪
Sprint 3 | Compartment 1: Market, Intake & Client POCs | S3.4 | Finalize written POC Scope: **Orane** | Yashvi | Thu, Sept 17 (Day 17) | [ ] Planned | Written scope document ready for Business & client sign-off | - | None | None | ⚪
Sprint 3 | Compartment 1: Market, Intake & Client POCs | S3.5 | Finalize written POC Scope: **College Vidya** | Yashvi | Thu, Sept 17 (Day 17) | [ ] Planned | Written scope document ready for Business & client sign-off | - | None | None | ⚪
Sprint 3 | Compartment 1: Market, Intake & Client POCs | S3.6 | Finalize written POC Scope: **Chitkara** | Yashvi | Fri, Sept 18 (Day 18) | [ ] Planned | Written scope document ready for Business & client sign-off | - | None | None | ⚪
Sprint 3 | Compartment 1: Market, Intake & Client POCs | S3.7 | **Secure 3 Accepted Written POC Scopes (M1)** | Yashvi | **Sun, Sept 20 (Day 20)** | [ ] Planned | **3 Written POC scopes accepted by client and Business** | - | None | None | ⚪
Sprint 3 | Compartment 1: Market, Intake & Client POCs | S3.8 | Mandatory intake process enforcement on all new leads | Prakhar | Daily | [ ] Planned | 100% of new client requests enter through standard intake | - | None | None | ⚪
Sprint 3 | Compartment 2: Product, In-House LMS & Demo Stabilisation | S3.9 | **In-House LMS Build (Part 2: Student OS & Progress Tracking)** | Shubham | Wed, Sept 16 (Day 16) | [ ] Planned | Student profile, module progress & analytics tracking module | - | None | None | ⚪
Sprint 3 | Compartment 2: Product, In-House LMS & Demo Stabilisation | S3.10 | **In-House LMS Integration with Mr. Learn & Mr. Test** | Shubham | Fri, Sept 18 (Day 18) | [ ] Planned | Working prototype connecting Mr. Learn UI to in-house LMS | - | None | None | ⚪
Sprint 3 | Compartment 2: Product, In-House LMS & Demo Stabilisation | S3.11 | Create short 15-min demo flow/script per suite | Shubham | Wed, Sept 16 (Day 16) | [ ] Planned | Business-ready demo flow & narrative scripts | - | None | None | ⚪
Sprint 3 | Compartment 2: Product, In-House LMS & Demo Stabilisation | S3.12 | **Demo #3: Sales & Admin Suite Walkthrough** | Prakhar | **Thu, Sept 17 (Day 17)** | [ ] Planned | **Weekday demo of Sales & Admin Suite** | - | None | None | ⚪
Sprint 3 | Compartment 2: Product, In-House LMS & Demo Stabilisation | S3.13 | Start QA regression test suite on P0 products | QA / Tester | Fri, Sept 18 (Day 18) | [ ] Planned | Regression test cases drafted and executing | - | None | None | ⚪
Sprint 3 | Compartment 3: Cloud, Cost & Internal Automation | S3.14 | Restructure cloud projects & accounts where required | Rohan | Tue, Sept 15 (Day 15) | [ ] Planned | Clean logical separation across GCP/AWS | - | None | None | ⚪
Sprint 3 | Compartment 3: Cloud, Cost & Internal Automation | S3.15 | Separate dev / demo / production environments | Rohan | Thu, Sept 17 (Day 17) | [ ] Planned | Isolated demo environment preventing test contamination | - | None | None | ⚪
Sprint 3 | Compartment 3: Cloud, Cost & Internal Automation | S3.16 | Select top 1 simple, high-value departmental workflow | Rohan | Wed, Sept 16 (Day 16) | [ ] Planned | Target automation selected for Month 1 build | - | None | None | ⚪
Sprint 3 | Compartment 3: Cloud, Cost & Internal Automation | S3.17 | Build & test first internal automation workflow prototype | Rohan | Fri, Sept 18 (Day 18) | [ ] Planned | Core automation script/integration built | - | None | None | ⚪
Sprint 3 | Compartment 3: Cloud, Cost & Internal Automation | S3.18 | **Switch on AI Cost Instrumentation Baseline (M4)** | Rohan | **Mon, Sept 21 (Day 21)** | [ ] Planned | **Product-level token/API spend visible for live workloads** | - | None | None | ⚪
Sprint 3 | Compartment 4: Leadership, Compute & Enablers | S3.19 | Advance GPU compute/vendor discussions with Sajan | Gaurav | Thu, Sept 17 (Day 17) | [ ] Planned | Hardware spec options, vendor terms, and cost projection | - | None | None | ⚪
Sprint 3 | Compartment 4: Leadership, Compute & Enablers | S3.20 | **Weekly Product & Capability Review #3 (8:00 PM)** | Gaurav | Fri, Sept 18 (Day 18) | [ ] Planned | Review minutes, LMS Prototype Part 2 preview & ad-hoc audit | - | None | None | ⚪
Sprint 3 | Compartment 4: Leadership, Compute & Enablers | S3.21 | **Onboard QA Tester & PM Intern (M8)** | Gaurav | **Mon, Sept 21 (Day 21)** | [ ] Planned | **QA active on P0 regression; Intern active on tasks** | - | None | None | ⚪
Sprint 4 | Compartment 1: Market, Intake & Client POCs | S4.1 | Hand over accepted POC scopes to Tech Lead | Yashvi | Tue, Sept 22 (Day 22) | [ ] Planned | Clear deployment handoff for Orane, CV, Chitkara | - | None | None | ⚪
Sprint 4 | Compartment 1: Market, Intake & Client POCs | S4.2 | Deploy PM Intern on catalogue & client tracking | Yashvi | Thu, Sept 24 (Day 24) | [ ] Planned | PM Intern operational on tracking & meeting logs | - | None | None | ⚪
Sprint 4 | Compartment 1: Market, Intake & Client POCs | S4.3 | Publish Month 2 Backlog (including Externalisation Gap Sheet) | Prakhar | Sat, Sept 26 (Day 26) | [ ] Planned | Prioritized engineering sprint backlog for Month 2 | - | None | None | ⚪
Sprint 4 | Compartment 2: Product, In-House LMS & Demo Stabilisation | S4.4 | Execute full demo dry-runs with QA on both live suites | Shubham | Wed, Sept 23 (Day 23) | [ ] Planned | End-to-end regression & flow validation pass | - | None | None | ⚪
Sprint 4 | Compartment 2: Product, In-House LMS & Demo Stabilisation | S4.5 | **Demo #4: Learning Suite Walkthrough (with LMS Prototype)** | Yashvi | **Thu, Sept 24 (Day 24)** | [ ] Planned | **Weekday demo of Learning Suite with In-House LMS Preview** | - | None | None | ⚪
Sprint 4 | Compartment 2: Product, In-House LMS & Demo Stabilisation | S4.6 | Fix all remaining demo and staging edge cases | Rohan | Thu, Sept 24 (Day 24) | [ ] Planned | Zero critical bugs; staging rock solid | - | None | None | ⚪
Sprint 4 | Compartment 2: Product, In-House LMS & Demo Stabilisation | S4.7 | **P0 Stabilisation & Demo Readiness Sign-Off (M2)** | Shubham | **Fri, Sept 25 (Day 25)** | [ ] Planned | **100% of P0 products demo-able on 24h notice; zero critical bugs** | - | None | None | ⚪
Sprint 4 | Compartment 3: Cloud, Cost & Internal Automation | S4.8 | **Document final GCP + AWS architecture & ownership** | Rohan | **Fri, Sept 25 (Day 25)** | [ ] Planned | Shared cloud infra map with cost attribution by product | - | None | None | ⚪
Sprint 4 | Compartment 3: Cloud, Cost & Internal Automation | S4.9 | Deploy & test internal automation with actual department users | Rohan | Fri, Sept 25 (Day 25) | [ ] Planned | Live end-to-end workflow execution | - | None | None | ⚪
Sprint 4 | Compartment 3: Cloud, Cost & Internal Automation | S4.10 | Measure baseline vs post-automation hours saved per week | Rohan | Mon, Sept 28 (Day 28) | [ ] Planned | Measured internal service value metric | - | None | None | ⚪
Sprint 4 | Compartment 3: Cloud, Cost & Internal Automation | S4.11 | **Launch First Internal AI Automation Workflow Live (M7)** | Rohan | **Mon, Sept 28 (Day 28)** | [ ] Planned | **Workflow live in production; weekly hours saved tracked** | - | None | None | ⚪
Sprint 4 | Compartment 4: Leadership, Compute & Enablers | S4.12 | **Weekly Review #4: P0 Demo Readiness Sign-off (8:00 PM)** | Gaurav | Fri, Sept 25 (Day 25) | [ ] Planned | Review minutes, Demo sign-off & LMS prototype verification | - | None | None | ⚪
Sprint 4 | Compartment 4: Leadership, Compute & Enablers | S4.13 | **Finalize September GPU / Compute Setup Track (M10)** | Gaurav | **Wed, Sept 30 (Day 30)** | [ ] Planned | **Compute option, vendor contact, architecture & cost plan ready** | - | None | None | ⚪
Sprint 4 | Compartment 4: Leadership, Compute & Enablers | S4.14 | **MAS AI Labs Website & Info ID Live (M11)** | Marketing / Vendor | **Wed, Sept 30 (Day 30)** | [ ] Planned | **Website live + Info ID routed to named owner** | - | None | None | ⚪
Sprint 4 | Compartment 4: Leadership, Compute & Enablers | S4.15 | Close 3 financial baselines (Revenue target, run-rate, hiring) | Gaurav | Wed, Sept 30 (Day 30) | [ ] Planned | Closed financial baselines with Jitin Sir & Pranab Sir | - | None | None | ⚪
Sprint 4 | Compartment 4: Leadership, Compute & Enablers | S4.16 | **Publish Month-End Management Report & Month 2 Backlog** | Gaurav | **Wed, Sept 30 (Day 30)** | [ ] Planned | **Comprehensive Month 1 closure report & Month 2 plan** | - | None | None | ⚪

## Sprint 1
Compartment | Task ID | Task / Activity | Lead Owner | Target Date | Status | Expected Outcome | Actual Outcome | Blocker | Delay Reason | RAG
Compartment 1: Market, Intake & Client POCs | S1.1 | Draft Business $\rightarrow$ Tech Intake Format v1 | Prakhar | Thu, Sept 3 (Day 3) | [-] In Progress | Standard intake format defining: Who $\rightarrow$ Wants What $\rightarrow$ Context $\rightarrow$ POC $\rightarrow$ Scale $\rightarrow$ Tech expectation | Creating client contact intake sheet in Google Sheet format | None | None | 🟡
Compartment 1: Market, Intake & Client POCs | S1.2 | Collect client context: **Orane** | Yashvi | Fri, Sept 4 (Day 4) | [ ] Planned | Complete background, target audience, scale, missing items identified | Will start today | None | None | ⚪
Compartment 1: Market, Intake & Client POCs | S1.3 | Collect client context: **College Vidya** | Yashvi | Fri, Sept 4 (Day 4) | [ ] Planned | Complete admissions/CRM context, scale, integration requirements | Will start today | None | None | ⚪
Compartment 1: Market, Intake & Client POCs | S1.4 | Collect client context: **Chitkara** | Yashvi | Fri, Sept 4 (Day 4) | [ ] Planned | Complete placement/academic scope, 100-student cohort context | Will start today | None | None | ⚪
Compartment 1: Market, Intake & Client POCs | S1.5 | Define schema & draft **Product Catalogue v1** | Prakhar | Fri, Sept 4 (Day 4) | [ ] Planned | Product, buyer, use case, maturity, demo readiness, limitations | - | None | None | ⚪
Compartment 1: Market, Intake & Client POCs | S1.6 | Define schema & seed **Capability Registry v1** | Yashvi | Fri, Sept 4 (Day 4) | [x] Completed | Core AI capabilities (RAG, Eval, Voice, Parser) mapped to products | Need to update it at end of the month | None | None | 🟢
Compartment 2: Product, In-House LMS & Demo Stabilisation | S1.7 | Freeze P0 product/module list & assign owners | Shubham | Wed, Sept 2 (Day 2) | [x] Completed | Final P0 list with named module owners across both suites | - | None | None | 🟢
Compartment 2: Product, In-House LMS & Demo Stabilisation | S1.8 | Triage all P0 bugs across live suites by severity | Shubham | Wed, Sept 2 (Day 2) | [ ] Planned | Critical / blocker bug list ready with reproduction steps | - | None | None | ⚪
Compartment 2: Product, In-House LMS & Demo Stabilisation | S1.9 | **Fix critical / blocking P0 bugs on staging** | Rohan | **Fri, Sept 4 (Day 4)** | [-] In Progress | **Critical blocker issues cleared in Week 1; verified** | Email delivery bug fixed; info email account migrated; testing pipeline | GPT credit exhausted | None | 🔴
Compartment 2: Product, In-House LMS & Demo Stabilisation | S1.10 | Define clean demo environment requirements | Shubham | Fri, Sept 4 (Day 4) | [ ] Planned | Spec sheet for dummy student rosters & sanitized CRM leads | - | None | None | ⚪
Compartment 2: Product, In-House LMS & Demo Stabilisation | S1.11 | **Demo #1: Sales & Admin Suite Walkthrough** | Prakhar | **Thu, Sept 3 (Day 3)** | [ ] Planned | **Weekday baseline demo of Sales & Admin Suite** | - | None | None | ⚪
Compartment 2: Product, In-House LMS & Demo Stabilisation | S1.22 | Sales Suite technical documentation & research plan | Shubham | Fri, Sept 4 (Day 4) | [x] Completed | Technical architecture doc & generalized setup plan | Sales Suite prototype presented (DB separation & lead import); backend analysis underway | None | None | 🟢
Compartment 3: Cloud, Cost & Internal Automation | S1.12 | Inventory current GCP projects, services & VMs | Rohan | Thu, Sept 3 (Day 3) | [!] Blocked | Complete GCP infrastructure inventory with instance sizes | - | GPT credit exhausted | None | 🔴
Compartment 3: Cloud, Cost & Internal Automation | S1.13 | Inventory AWS accounts/services used by AI Labs | Rohan | Fri, Sept 4 (Day 4) | [ ] Planned | Complete AWS inventory (S3, compute, IAM) | - | GPT credit exhausted | None | 🔴
Compartment 3: Cloud, Cost & Internal Automation | S1.14 | Master inventory of AI/API keys, models & endpoints | Rohan | Fri, Sept 4 (Day 4) | [ ] Planned | All third-party AI keys mapped to product modules | - | GPT credit exhausted | None | 🔴
Compartment 3: Cloud, Cost & Internal Automation | S1.15 | Collect top repetitive workflows across MAS departments | Rohan | Fri, Sept 4 (Day 4) | [ ] Planned | Departmental automation intake list (Problem $\rightarrow$ Effort $\rightarrow$ Value) | - | GPT credit exhausted | None | 🔴
Compartment 3: Cloud, Cost & Internal Automation | S1.16 | **Build & configure MAS Slack Standup Bot v1.0** | Yashvi | **Thu, Sept 3 (Day 3)** | [-] In Progress | **Personal DMs, dropdown modal, 7:45 PM summary & 2-way sync** | slack bot formatting fixing in progress | None | None | 🟡
Compartment 3: Cloud, Cost & Internal Automation | S1.17 | **Test & pilot Slack Standup Bot with core team** | Yashvi | **Fri, Sept 4 (Day 4)** | [-] In Progress | **Live test during Friday standup & Friday review #1** | Testing daily summaries and improve the AI summarisation | None | None | 🟡
Compartment 4: Leadership, Compute & Enablers | S1.18 | Kick off QA Tester (contract/2-mo) hiring | Gaurav | Tue, Sept 1 (Day 1) | [-] In Progress | Active job description & candidate pipeline with HR | - | None | None | 🟡
Compartment 4: Leadership, Compute & Enablers | S1.19 | Kick off PM Intern (25 hrs/wk) hiring | Gaurav | Tue, Sept 1 (Day 1) | [ ] Planned | Active job description & candidate sourcing | - | None | None | ⚪
Compartment 4: Leadership, Compute & Enablers | S1.20 | Initial September GPU/compute sync with Sajan | Gaurav | Thu, Sept 3 (Day 3) | [ ] Planned | Compute vendor contacts & initial workload candidate list | - | None | None | ⚪
Compartment 4: Leadership, Compute & Enablers | S1.21 | **Weekly Product & Capability Review #1 (8:00 PM)** | Gaurav | Fri, Sept 4 (Day 4) | [ ] Planned | Review minutes, Week 1 bug fix verification & RAG audit | - | None | None | ⚪

## Sprint 2
Compartment | Task ID | Task / Activity | Lead Owner | Target Date | Status | Expected Outcome | Actual Outcome | Blocker | Delay Reason | RAG
Compartment 1: Market, Intake & Client POCs | S2.1 | Walkthrough Intake Process with Pranab Sir | Prakhar | Mon, Sept 7 (Day 7) | [ ] Planned | Business alignment on mandatory intake rules | - | None | None | ⚪
Compartment 1: Market, Intake & Client POCs | S2.2 | **Sign off Business $\rightarrow$ Tech Intake Format (M6)** | Prakhar | **Thu, Sept 10 (Day 10)** | [ ] Planned | **Joint intake format signed off; live for Fri, Sept 11** | - | None | None | ⚪
Compartment 1: Market, Intake & Client POCs | S2.3 | Conduct structured scoping call: **Orane** | Yashvi | Tue, Sept 8 (Day 8) | [ ] Planned | Scope v1 draft for Orane (scale, features, timeline) | - | None | None | ⚪
Compartment 1: Market, Intake & Client POCs | S2.4 | Conduct structured scoping call: **College Vidya** | Yashvi | Wed, Sept 9 (Day 9) | [ ] Planned | Scope v1 draft for College Vidya (CRM/voice needs) | - | None | None | ⚪
Compartment 1: Market, Intake & Client POCs | S2.5 | Conduct structured scoping call: **Chitkara** | Yashvi | Thu, Sept 10 (Day 10) | [ ] Planned | Scope v1 draft for Chitkara (100-student placement cohort) | - | None | None | ⚪
Compartment 1: Market, Intake & Client POCs | S2.6 | Consolidate 3 Client Scope v1 drafts | Yashvi | Fri, Sept 11 (Day 11) | [ ] Planned | 3 Scopes ready for technical feasibility review | - | None | None | ⚪
Compartment 1: Market, Intake & Client POCs | S2.7 | Finalize & format **Product Catalogue v1** | Prakhar | Fri, Sept 11 (Day 11) | [ ] Planned | Published catalogue ready for official release (Due Sept 14) | - | None | None | ⚪
Compartment 1: Market, Intake & Client POCs | S2.8 | Finalize & format **Capability Registry v1** | Yashvi | Fri, Sept 11 (Day 11) | [ ] Planned | Seed registry ready for official release (Due Sept 14) | - | None | None | ⚪
Compartment 2: Product, In-House LMS & Demo Stabilisation | S2.9 | **In-House LMS Architecture & Data Schema Design** | Shubham | Tue, Sept 8 (Day 8) | [ ] Planned | Technical architecture spec for replacing Graphy in Mr. Learn | - | None | None | ⚪
Compartment 2: Product, In-House LMS & Demo Stabilisation | S2.10 | **In-House LMS Core Build (Part 1: Course & Content Engine)** | Shubham | Fri, Sept 11 (Day 11) | [ ] Planned | In-house course structure, modules & video delivery service | - | None | None | ⚪
Compartment 2: Product, In-House LMS & Demo Stabilisation | S2.11 | Curate clean demo environment: **Learning Suite** | Shubham | Wed, Sept 9 (Day 9) | [ ] Planned | Seeded with safe, client-presentable student data | - | None | None | ⚪
Compartment 2: Product, In-House LMS & Demo Stabilisation | S2.12 | Curate clean demo environment: **Sales CRM** | Shubham | Thu, Sept 10 (Day 10) | [ ] Planned | Stripped of internal MAS lead data; clean CRM pipeline | - | None | None | ⚪
Compartment 2: Product, In-House LMS & Demo Stabilisation | S2.13 | **Demo #2: Learning Suite Walkthrough** | Yashvi | **Wed, Sept 9 (Day 9)** | [ ] Planned | **Weekday baseline demo of Learning Suite** | - | None | None | ⚪
Compartment 3: Cloud, Cost & Internal Automation | S2.14 | Identify idle, duplicate, orphaned cloud resources | Rohan | Mon, Sept 7 (Day 7) | [ ] Planned | Cloud cleanup action list (disks, IPs, test VMs) | - | None | None | ⚪
Compartment 3: Cloud, Cost & Internal Automation | S2.15 | Clean up unused resources & permissions in GCP/AWS | Rohan | Tue, Sept 8 (Day 8) | [ ] Planned | Reduced waste & cleaner cloud estate | - | None | None | ⚪
Compartment 3: Cloud, Cost & Internal Automation | S2.16 | Apply naming, ownership and cost tagging to cloud assets | Rohan | Wed, Sept 9 (Day 9) | [ ] Planned | Resources traceable by product and environment | - | None | None | ⚪
Compartment 3: Cloud, Cost & Internal Automation | S2.17 | Prototype token & latency tracking helper / middleware | Rohan | Thu, Sept 10 (Day 10) | [ ] Planned | Request-level token logging on suite endpoints | - | None | None | ⚪
Compartment 3: Cloud, Cost & Internal Automation | S2.18 | Score collected departmental automation workflows | Rohan | Fri, Sept 11 (Day 11) | [ ] Planned | Workflows ranked by effort, impact, hours saved | - | None | None | ⚪
Compartment 3: Cloud, Cost & Internal Automation | S2.19 | **Full live pod rollout of Slack Standup Bot** | Yashvi | **Mon, Sept 7 (Day 7)** | [ ] Planned | **100% daily standup updates captured via Slack DMs & synced** | - | None | None | ⚪
Compartment 3: Cloud, Cost & Internal Automation | S2.20 | **Add /standup-notes & weekend rollover handler** | Yashvi | **Thu, Sept 10 (Day 10)** | [ ] Planned | **Post-call highlight logger and weekend rollover features live** | - | None | None | ⚪
Compartment 4: Leadership, Compute & Enablers | S2.21 | Screen resumes & interview QA Tester candidates | Gaurav | Wed, Sept 9 (Day 9) | [ ] Planned | QA candidate shortlisted & evaluated | - | None | None | ⚪
Compartment 4: Leadership, Compute & Enablers | S2.22 | Screen resumes & interview PM Intern candidates | Gaurav | Wed, Sept 9 (Day 9) | [ ] Planned | PM Intern candidate evaluated | - | None | None | ⚪
Compartment 4: Leadership, Compute & Enablers | S2.23 | Extend offers for QA Tester and PM Intern | Gaurav | Fri, Sept 11 (Day 11) | [ ] Planned | Offers extended for Sept 21 onboarding | - | None | None | ⚪
Compartment 4: Leadership, Compute & Enablers | S2.24 | Define GPU model-serving architecture with Sajan | Gaurav | Thu, Sept 10 (Day 10) | [ ] Planned | API vs Self-hosted cost comparison note | - | None | None | ⚪
Compartment 4: Leadership, Compute & Enablers | S2.25 | **Weekly Review #2: Month 1 Mid-Point Sign-off** | Gaurav | Fri, Sept 11 (Day 11) | [ ] Planned | Intake sign-off confirmed; LMS Build Part 1 progress review | - | None | None | ⚪

## Sprint 3
Compartment | Task ID | Task / Activity | Lead Owner | Target Date | Status | Expected Outcome | Actual Outcome | Blocker | Delay Reason | RAG
Compartment 1: Market, Intake & Client POCs | S3.1 | **Publish Product Catalogue v1 (M5)** | Prakhar | **Mon, Sept 14 (Day 14)** | [ ] Planned | **Catalogue v1 complete & published for Business** | - | None | None | ⚪
Compartment 1: Market, Intake & Client POCs | S3.2 | **Publish Capability Registry v1 (M5)** | Yashvi | **Mon, Sept 14 (Day 14)** | [ ] Planned | **Registry v1 seeded & published for Business** | - | None | None | ⚪
Compartment 1: Market, Intake & Client POCs | S3.3 | Conduct technical feasibility review on 3 client scopes | Shubham | Wed, Sept 16 (Day 16) | [ ] Planned | Feasibility note & rough effort estimate per client | - | None | None | ⚪
Compartment 1: Market, Intake & Client POCs | S3.4 | Finalize written POC Scope: **Orane** | Yashvi | Thu, Sept 17 (Day 17) | [ ] Planned | Written scope document ready for Business & client sign-off | - | None | None | ⚪
Compartment 1: Market, Intake & Client POCs | S3.5 | Finalize written POC Scope: **College Vidya** | Yashvi | Thu, Sept 17 (Day 17) | [ ] Planned | Written scope document ready for Business & client sign-off | - | None | None | ⚪
Compartment 1: Market, Intake & Client POCs | S3.6 | Finalize written POC Scope: **Chitkara** | Yashvi | Fri, Sept 18 (Day 18) | [ ] Planned | Written scope document ready for Business & client sign-off | - | None | None | ⚪
Compartment 1: Market, Intake & Client POCs | S3.7 | **Secure 3 Accepted Written POC Scopes (M1)** | Yashvi | **Sun, Sept 20 (Day 20)** | [ ] Planned | **3 Written POC scopes accepted by client and Business** | - | None | None | ⚪
Compartment 1: Market, Intake & Client POCs | S3.8 | Mandatory intake process enforcement on all new leads | Prakhar | Daily | [ ] Planned | 100% of new client requests enter through standard intake | - | None | None | ⚪
Compartment 2: Product, In-House LMS & Demo Stabilisation | S3.9 | **In-House LMS Build (Part 2: Student OS & Progress Tracking)** | Shubham | Wed, Sept 16 (Day 16) | [ ] Planned | Student profile, module progress & analytics tracking module | - | None | None | ⚪
Compartment 2: Product, In-House LMS & Demo Stabilisation | S3.10 | **In-House LMS Integration with Mr. Learn & Mr. Test** | Shubham | Fri, Sept 18 (Day 18) | [ ] Planned | Working prototype connecting Mr. Learn UI to in-house LMS | - | None | None | ⚪
Compartment 2: Product, In-House LMS & Demo Stabilisation | S3.11 | Create short 15-min demo flow/script per suite | Shubham | Wed, Sept 16 (Day 16) | [ ] Planned | Business-ready demo flow & narrative scripts | - | None | None | ⚪
Compartment 2: Product, In-House LMS & Demo Stabilisation | S3.12 | **Demo #3: Sales & Admin Suite Walkthrough** | Prakhar | **Thu, Sept 17 (Day 17)** | [ ] Planned | **Weekday demo of Sales & Admin Suite** | - | None | None | ⚪
Compartment 2: Product, In-House LMS & Demo Stabilisation | S3.13 | Start QA regression test suite on P0 products | QA / Tester | Fri, Sept 18 (Day 18) | [ ] Planned | Regression test cases drafted and executing | - | None | None | ⚪
Compartment 3: Cloud, Cost & Internal Automation | S3.14 | Restructure cloud projects & accounts where required | Rohan | Tue, Sept 15 (Day 15) | [ ] Planned | Clean logical separation across GCP/AWS | - | None | None | ⚪
Compartment 3: Cloud, Cost & Internal Automation | S3.15 | Separate dev / demo / production environments | Rohan | Thu, Sept 17 (Day 17) | [ ] Planned | Isolated demo environment preventing test contamination | - | None | None | ⚪
Compartment 3: Cloud, Cost & Internal Automation | S3.16 | Select top 1 simple, high-value departmental workflow | Rohan | Wed, Sept 16 (Day 16) | [ ] Planned | Target automation selected for Month 1 build | - | None | None | ⚪
Compartment 3: Cloud, Cost & Internal Automation | S3.17 | Build & test first internal automation workflow prototype | Rohan | Fri, Sept 18 (Day 18) | [ ] Planned | Core automation script/integration built | - | None | None | ⚪
Compartment 3: Cloud, Cost & Internal Automation | S3.18 | **Switch on AI Cost Instrumentation Baseline (M4)** | Rohan | **Mon, Sept 21 (Day 21)** | [ ] Planned | **Product-level token/API spend visible for live workloads** | - | None | None | ⚪
Compartment 4: Leadership, Compute & Enablers | S3.19 | Advance GPU compute/vendor discussions with Sajan | Gaurav | Thu, Sept 17 (Day 17) | [ ] Planned | Hardware spec options, vendor terms, and cost projection | - | None | None | ⚪
Compartment 4: Leadership, Compute & Enablers | S3.20 | **Weekly Product & Capability Review #3 (8:00 PM)** | Gaurav | Fri, Sept 18 (Day 18) | [ ] Planned | Review minutes, LMS Prototype Part 2 preview & ad-hoc audit | - | None | None | ⚪
Compartment 4: Leadership, Compute & Enablers | S3.21 | **Onboard QA Tester & PM Intern (M8)** | Gaurav | **Mon, Sept 21 (Day 21)** | [ ] Planned | **QA active on P0 regression; Intern active on tasks** | - | None | None | ⚪

## Sprint 4
Compartment | Task ID | Task / Activity | Lead Owner | Target Date | Status | Expected Outcome | Actual Outcome | Blocker | Delay Reason | RAG
Compartment 1: Market, Intake & Client POCs | S4.1 | Hand over accepted POC scopes to Tech Lead | Yashvi | Tue, Sept 22 (Day 22) | [ ] Planned | Clear deployment handoff for Orane, CV, Chitkara | - | None | None | ⚪
Compartment 1: Market, Intake & Client POCs | S4.2 | Deploy PM Intern on catalogue & client tracking | Yashvi | Thu, Sept 24 (Day 24) | [ ] Planned | PM Intern operational on tracking & meeting logs | - | None | None | ⚪
Compartment 1: Market, Intake & Client POCs | S4.3 | Publish Month 2 Backlog (including Externalisation Gap Sheet) | Prakhar | Sat, Sept 26 (Day 26) | [ ] Planned | Prioritized engineering sprint backlog for Month 2 | - | None | None | ⚪
Compartment 2: Product, In-House LMS & Demo Stabilisation | S4.4 | Execute full demo dry-runs with QA on both live suites | Shubham | Wed, Sept 23 (Day 23) | [ ] Planned | End-to-end regression & flow validation pass | - | None | None | ⚪
Compartment 2: Product, In-House LMS & Demo Stabilisation | S4.5 | **Demo #4: Learning Suite Walkthrough (with LMS Prototype)** | Yashvi | **Thu, Sept 24 (Day 24)** | [ ] Planned | **Weekday demo of Learning Suite with In-House LMS Preview** | - | None | None | ⚪
Compartment 2: Product, In-House LMS & Demo Stabilisation | S4.6 | Fix all remaining demo and staging edge cases | Rohan | Thu, Sept 24 (Day 24) | [ ] Planned | Zero critical bugs; staging rock solid | - | None | None | ⚪
Compartment 2: Product, In-House LMS & Demo Stabilisation | S4.7 | **P0 Stabilisation & Demo Readiness Sign-Off (M2)** | Shubham | **Fri, Sept 25 (Day 25)** | [ ] Planned | **100% of P0 products demo-able on 24h notice; zero critical bugs** | - | None | None | ⚪
Compartment 3: Cloud, Cost & Internal Automation | S4.8 | **Document final GCP + AWS architecture & ownership** | Rohan | **Fri, Sept 25 (Day 25)** | [ ] Planned | Shared cloud infra map with cost attribution by product | - | None | None | ⚪
Compartment 3: Cloud, Cost & Internal Automation | S4.9 | Deploy & test internal automation with actual department users | Rohan | Fri, Sept 25 (Day 25) | [ ] Planned | Live end-to-end workflow execution | - | None | None | ⚪
Compartment 3: Cloud, Cost & Internal Automation | S4.10 | Measure baseline vs post-automation hours saved per week | Rohan | Mon, Sept 28 (Day 28) | [ ] Planned | Measured internal service value metric | - | None | None | ⚪
Compartment 3: Cloud, Cost & Internal Automation | S4.11 | **Launch First Internal AI Automation Workflow Live (M7)** | Rohan | **Mon, Sept 28 (Day 28)** | [ ] Planned | **Workflow live in production; weekly hours saved tracked** | - | None | None | ⚪
Compartment 4: Leadership, Compute & Enablers | S4.12 | **Weekly Review #4: P0 Demo Readiness Sign-off (8:00 PM)** | Gaurav | Fri, Sept 25 (Day 25) | [ ] Planned | Review minutes, Demo sign-off & LMS prototype verification | - | None | None | ⚪
Compartment 4: Leadership, Compute & Enablers | S4.13 | **Finalize September GPU / Compute Setup Track (M10)** | Gaurav | **Wed, Sept 30 (Day 30)** | [ ] Planned | **Compute option, vendor contact, architecture & cost plan ready** | - | None | None | ⚪
Compartment 4: Leadership, Compute & Enablers | S4.14 | **MAS AI Labs Website & Info ID Live (M11)** | Marketing / Vendor | **Wed, Sept 30 (Day 30)** | [ ] Planned | **Website live + Info ID routed to named owner** | - | None | None | ⚪
Compartment 4: Leadership, Compute & Enablers | S4.15 | Close 3 financial baselines (Revenue target, run-rate, hiring) | Gaurav | Wed, Sept 30 (Day 30) | [ ] Planned | Closed financial baselines with Jitin Sir & Pranab Sir | - | None | None | ⚪
Compartment 4: Leadership, Compute & Enablers | S4.16 | **Publish Month-End Management Report & Month 2 Backlog** | Gaurav | **Wed, Sept 30 (Day 30)** | [ ] Planned | **Comprehensive Month 1 closure report & Month 2 plan** | - | None | None | ⚪